## Sheet1
Story | Points | Assigned To | Sprint | Status | Date | Completed By
Requirement Analysis | 5 | Jeyasri, Subarna, Pranav, Wasae | Sprint 1 | Complete | 2020-03-07 | Jeyasri, Subarna, Pranav, Wasae
Technology Design | 5 | Jeyasri, Subarna, Pranav, Wasae | Sprint 1 | Complete | 2020-03-07 | Jeyasri, Subarna, Pranav, Wasae
Database Design | 5 | Jeyasri, Subarna, Pranav, Wasae | Sprint 1 | Complete | 2020-03-07 | Jeyasri, Subarna, Pranav, Wasae
Class Design | 5 | Jeyasri, Subarna, Pranav, Wasae | Sprint 1 | Complete | 2020-03-07 | Jeyasri, Subarna, Pranav, Wasae
Basic design for backend | 1 | Jeyasri | Sprint 1 | Complete | 2020-03-07 | Jeyasri
Backend Design | 5 | Pranav, Wasae | Sprint 2 | Complete | 2020-03-15 | Pranav, Wasae
Setup AngularJS | 2 | Jeyasri | Sprint 2 | Complete | 2020-03-15 | Jeyasri
Setup Spring Boot | 2 | Subarna | Sprint 2 | Complete | 2020-03-15 | Subarna
Setup SQL script | 3 | Pranav | Sprint 2 | Complete | 2020-03-15 | Pranav
Wireframe | 5 | Jeyasri | Sprint 2 | Complete | 2020-03-15 | Jeyasri, Subarna, Pranav, Wasae
Setup Infra | 2 | Wasae | Sprint 2 | Complete | 2020-03-15 | Wasae
Infrastructure Design | 5 | Wasae | Sprint 2 | Complete | 2020-03-15 | Wasae
Setup our GitHub | 1 | Jeyasri, Subarna, Pranav, Wasae | Sprint 2 | Complete | 2020-03-15 | Jeyasri, Subarna, Pranav, Wasae
User Authentication API | 3 | Wasae/Pranav | Sprint 3 | Complete | 2020-03-22 | Wasae/Pranav
Registration API | 5 | Wasae/Pranav | Spring 3 | Complete | 2020-03-22 | Wasae/Pranav
Add Vehicle API | 3 | Subarna | Spring 3 | Complete | 2020-03-22 | Subarna
Update Vehicle API | 3 | Subarna | Spring 3 | Complete | 2020-03-22 | Subarna
Get By Id- Vehicle API | 4 | Subarna | Spring 3 | Complete | 2020-03-22 | Subarna
Get Vehicle API | 1 | Subarna | Sprint 4 | Complete | 2020-03-29 | Subarna
Get Vehicle for a fixed VehicleType API | 1 | Subarna | Sprint 4 | Complete | 2020-03-29 | Subarna
Get Vehicles from a Location Type | 1 | Subarna | Sprint 4 | Complete | 2020-03-29 | Subarna
Remove Vehicle API | 5 | Subarna | Sprint 4 | Complete | 2020-03-29 | Subarna
Add Location API | 4 | Subarna | sprint 5 | Complete | 2020-04-05 | Subarna
Get Location API | 1 | Subarna | sprint 5 | Complete | 2020-04-05 | Subarna
Update Location API | 3 | Subarna | sprint 5 | Complete | 2020-04-05 | Subarna
Remove Location API | 2 | Subarna | sprint 5 | Complete | 2020-04-05 | Subarna
Get By Id- Location API | 2 | Subarna | sprint 6 | Complete | 2020-04-12 | Subarna
Add User API | 1 | Wasae/Pranav | sprint 6 | Complete | 2020-04-12 | Wasae/Pranav
Update User API | 1 | Wasae/Pranav | sprint 6 | Complete | 2020-04-12 | Wasae/Pranav
Remove User API | 5 | Wasae/Pranav | sprint 6 | Complete | 2020-04-12 | Wasae/Pranav
Add Column Status in rervation table | 4 | Pranav | sprint 7 | Complete | 2020-04-19 | Pranav
Add column description to price | 2 | Pranav | sprint 7 | Complete | 2020-04-19 | Pranav
Add CreditCard to Customer | 3 | Pranav | sprint 7 | Complete | 2020-04-19 | Pranav
Get Price API | 3 | Wasae/Pranav | sprint 7 | Complete | 2020-04-19 | Wasae/Pranav
Add Price API | 3 | Wasae/Pranav | sprint 8 | Complete | 2020-04-26 | Wasae/Pranav
Update Price API | 3 | Wasae/Pranav | sprint 8 | Complete | 2020-04-26 | Wasae/Pranav
Remove Price API | 1 | Wasae/Pranav | sprint 8 | Complete | 2020-04-26 | Wasae/Pranav
Get Damage API | 5 | Wasae/Pranav | sprint 8 | Complete | 2020-04-26 | Wasae/Pranav
Add Damage API | 4 | Wasae/Pranav | sprint 9 | Complete | 2020-05-07 | Wasae/Pranav
Remove Damage API | 5 | Wasae/Pranav | sprint 9 | Complete | 2020-05-07 | Wasae/Pranav
Update Damage API | 4 | Wasae/Pranav | sprint 9 | Complete | 2020-05-07 | Wasae/Pranav
Add Reservation API | 3 | Subarna | sprint 9 | Complete | 2020-05-07 | Subarna
Get Reservation API | 3 | Subarna | sprint 9 | Complete | 2020-05-07 | Subarna
Get by Id Reservation API | 4 | Subarna | sprint 9 | Complete | 2020-05-07 | Subarna
Update Reservation API | 4 | Subarna | sprint 9 | Complete | 2020-05-07 | Subarna
Cancel Reservation API with lateFee computation | 5 | Subarna | sprint 9 | Complete | 2020-05-07 | Subarna
Cancel Reservation API without lateFee | 3 | Subarna | sprint 9 | Complete | 2020-05-07 | Subarna
Invoice computation API (PUT) | 4 | Subarna | sprint 9 | Complete | 2020-05-07 | Subarna
Invoice get all API | 4 | Subarna | sprint 9 | Complete | 2020-05-07 | Subarna
Invoice get by Id API | 2 | Subarna | sprint 9 | Complete | 2020-05-07 | Subarna
Cancel Membership API | 4 | Wasae/Pranav | sprint 9 | Complete | 2020-05-07 | Wasae/Pranav
Renew Membership API | 1 | Wasae/Pranav | sprint 9 | Complete | 2020-05-07 | Wasae/Pranav
Get VehicleType API | 3 | Wasae/Pranav | sprint 9 | Complete | 2020-05-07 | Wasae/Pranav
Update VehicleType API | 3 | Wasae/Pranav | sprint 9 | Complete | 2020-05-07 | Wasae/Pranav
Add VehicleType API | 3 | Wasae/Pranav | sprint 9 | Complete | 2020-05-07 | Wasae/Pranav
Remove VehicleType API | 3 | Wasae/Pranav | sprint 9 | Complete | 2020-05-07 | Wasae/Pranav
Get Employee API | 1 | Wasae/Pranav | sprint 9 | Complete | 2020-05-07 | Wasae/Pranav
Add Employee API | 2 | Wasae/Pranav | sprint 9 | Complete | 2020-05-07 | Wasae/Pranav
UpdateEmployee API | 3 | Wasae/Pranav | sprint 9 | Complete | 2020-05-07 | Wasae/Pranav
DeleteEmployee API | 3 | Wasae/Pranav | sprint 9 | Complete | 2020-05-07 | Wasae/Pranav
Special api to compute the estimated prices for all the available vehicles in a location for all vehicle types | 1 | Subarna | sprint 9 | Complete | 2020-05-07 | Subarna
get available vehicle list for a vehicleType Id, location, and non overlapping pickuptime, actualdropOfftime from reservation | 1 | Subarna | sprint 9 | Complete | 2020-05-07 | Subarna
Update vehicle APIs and related code for new columns | 3 | Subarna | sprint 9 | Complete | 2020-05-07 | Subarna
Setup front end routing | 5 | Jeyasri | sprint 9 | Complete | 2020-05-07 | Jeyasri
Connect backend and frontend | 4 | Jeyasri | sprint 9 | Complete | 2020-05-07 | Jeyasri
Save User Session token | 2 | Jeyasri | sprint 9 | Complete | 2020-05-07 | Jeyasri
Login Page | 1 | Jeyasri | Spring 3 | Complete | 2020-03-22 | Jeyasri
Signup Page | 5 | Jeyasri | Spring 3 | Complete | 2020-03-22 | Jeyasri
Profile Page | 3 | Jeyasri | Spring 3 | Complete | 2020-03-22 | Jeyasri
Booking Page | 3 | Jeyasri | Sprint 4 | Complete | 2020-03-29 | Jeyasri
Reservation Page | 3 | Jeyasri | Sprint 4 | Complete | 2020-03-29 | Jeyasri
Search Page | 5 | Jeyasri | Sprint 4 | Complete | 2020-03-29 | Jeyasri
Book page (final page in booking process) | 4 | Jeyasri | Sprint 5 | Complete | 2020-04-05 | Jeyasri
Different pages for customer/admin | 5 | Jeyasri | Sprint 5 | Complete | 2020-04-05 | Jeyasri
List of Vehicles Page | 5 | Jeyasri | Sprint 5 | Complete | 2020-04-05 | Jeyasri
Individual Vehicle Page | 3 | Jeyasri | Sprint 5 | Complete | 2020-04-05 | Jeyasri
Add Vehicle Page | 5 | Jeyasri | sprint 6 | Complete | 2020-04-12 | Jeyasri
List of User Page | 2 | Jeyasri | sprint 6 | Complete | 2020-04-12 | Jeyasri
Individual User Page | 5 | Jeyasri | sprint 6 | Complete | 2020-04-12 | Jeyasri
Add User Page | 4 | Jeyasri | sprint 6 | Complete | 2020-04-12 | Jeyasri
List of Location Page | 2 | Jeyasri | sprint 7 | Complete | 2020-04-19 | Jeyasri
Individual Location Page | 2 | Jeyasri | sprint 8 | Complete | 2020-04-26 | Jeyasri
Add Location Page | 1 | Jeyasri | sprint 8 | Complete | 2020-04-26 | Jeyasri
List of Reservation Page | 4 | Jeyasri | sprint 8 | Complete | 2020-04-26 | Jeyasri
Add Reservation Page | 5 | Jeyasri | sprint 8 | Complete | 2020-05-07 | Jeyasri
269

## Sheet2
Sprint | Completed | Status
1 | 250 | 250
2 | 240 | 222.2222
3 | 200 | 194.4444
4 | 200 | 166.6667
5 | 150 | 138.8889
6 | 130 | 111.1111
7 | 100 | 83.3333
8 | 90 | 55.5556
9 | 70 | 27.7778
10 | 0 | 0