## Sheet1
Story | Description | Points | Assigned To | Sprint | Status | Link to work item | Comments/Description
Requirement Analysis | As a team, we want to understand the requirements so that we can implement a solution | 5 | Jeyasri, Subarna, Pranav, Wasae | Sprint 1 | Complete
Technology Design | As a team, we want to create a design for the project so that we can implement best design/practices for our solution | 5 | Jeyasri, Subarna, Pranav, Wasae | Sprint 1 | Complete
Database Design | As a team, we want to create database design for the project so we have a good outline of how to implement our solution | 5 | Jeyasri, Subarna, Pranav, Wasae | Sprint 1 | Complete
Class Design | As a team, we want to create class design for the project so we have a good outline of how to implement our solution | 5 | Jeyasri, Subarna, Pranav, Wasae | Sprint 1 | Complete
Basic design for backend | As a team, we want a basic idea for the backend design | 1 | Jeyasri | Sprint 1 | Complete
Backend Design | As a team, we want to design our api's so that we can build the correct api's for the project | 5 | Pranav, Wasae | Sprint 2 | Triaged
Setup AngularJS | As a developer, I want to setup the angular framework so that we can setup our frontend framework for the project | 2 | Jeyasri | Sprint 2 | Triaged
Setup Spring Boot | As a developer, I want to setup spring boot so that we can start writing backend code for the project | 2 | Subarna | Sprint 2 | Triaged
Setup SQL script | As a developer, I want to create a SQL script to quickly setup the tables in mysql | 3 | Pranav | Sprint 2 | Triaged
Wireframe | As a team, we want to design our wireframe flow so that we can understand the frontend flow and implement it | 5 | Jeyasri, Subarna, Pranav, Wasae | Sprint 2 | In Progress |  | Should we move this to the next sprint? Theres like too much to do this sprint...
Setup Infra | As a developer, I want to setup AWS/Docker so that we can host our services | 2 | Wasae | Sprint 2 | Complete | https://github.com/gopinathsjsu/sp20-cmpe-202-sec-49-team-project-themeansquares/tree/feature/infra-setup
Infrastructure Design | As a team, we want to design our infra so that we can build the correct infra for the project | 5 | Wasae | Sprint 2 | Complete | https://docs.google.com/drawings/d/1o5QlzHn5SBViEctCeXhgsuKeCkFNHIoELyCXvspDOIw/edit
Setup our GitHub | As a team, we want to setup our github repo and add our members so that we can store our code and collabrate with the team | 1 | Jeyasri, Subarna, Pranav, Wasae | Sprint 2 | Complete | https://github.com/gopinathsjsu/sp20-cmpe-202-sec-49-team-project-themeansquares
[DUPLICATE] Search Vehicle With Query Params API |  |  | Wasae/Pranav
Notification About Vehicle Return API (part of invoice) |  |  |  | (Subarna I gave you this because once the invoice is done, just send an email from there)
OO relationship in models - search on how to do? how the relationship will be mapped to database ? [R&D] |  |  | Subarna
User Authentication API |  |  | Wasae/Pranav
Registration API |  |  | Wasae
Add Vehicle API |  |  | Subarna |  |  |  | admin should be able to add vehicle info to database
Update Vehicle API |  |  | Subarna |  |  |  | want to do some fine tune
Get By Id- Vehicle API |  |  | Subarna
Get Vehicle API |  |  | Subarna
Get Vehicle for a fixed VehicleType API |  |  | Subarna
Get Vehicles from a Location Type |  |  | Subarna
Remove Vehicle API |  |  | Subarna
Add Location API |  |  | Subarna |  |  |  | * question- any validation?
Get Location API |  |  | Subarna
Update Location API |  |  | Subarna
Remove Location API |  |  | Subarna
Get By Id- Location API |  |  | Subarna
Add User API |  |  | Wasae/Pranav
Update User API |  |  | Wasae/Pranav
Remove User API |  |  | Wasae/Pranav
Add Column Status in rervation table |  |  | Pranav
Add column description to price |  |  | Pranav
Add CreditCard to Customer |  |  | Pranav
Get Price API |  |  | Wasae/Pranav
Add Price API |  |  | Wasae/Pranav
Update Price API |  |  | Wasae/Pranav
Remove Price API |  |  | Wasae/Pranav
Get Damage API |  |  | Wasae/Pranav
Add Damage API |  |  | Wasae/Pranav
Remove Damage API |  |  | Wasae/Pranav
Update Damage API |  |  | Wasae/Pranav
Add Reservation API |  |  | Subarna
Get Reservation API |  |  | Subarna
Get by Id Reservation API |  |  | Subarna
Update Reservation API |  |  | Subarna
Cancel Reservation API with lateFee computation |  |  | Subarna
Cancel Reservation API without lateFee |  |  | Subarna
Invoice computation API (PUT) |  |  | Subarna
Invoice get all API |  |  | Subarna
Invoice get by Id API |  |  | Subarna
Cancel Membership API |  |  | Wasae/Pranav
Renew Membership API |  |  | Wasae/Pranav
Get VehicleType API |  |  | Wasae/Pranav
Update VehicleType API |  |  | Wasae/Pranav
Add VehicleType API |  |  | Wasae/Pranav
Remove VehicleType API |  |  | Wasae/Pranav
Get Employee API |  |  | Wasae/Pranav
Add Employee API |  |  | Wasae/Pranav
UpdateEmployee API |  |  | Wasae/Pranav
DeleteEmployee API |  |  | Wasae/Pranav
Special api to compute the estimated prices for all the available vehicles in a location for all vehicle types |  |  | Subarna
get available vehicle list for a vehicleType Id, location, and non overlapping pickuptime, actualdropOfftime from reservation |  |  | Subarna
Bug Fix |  |  | Subarna/Jeyasri/Wasae/Pranav
Setup front end routing |  |  | Jeyasri
Frontend and backend integration work |  |  | Jeyasri
Save User Session token |  |  | Jeyasri
Login Page |  |  | Jeyasri
Signup Page |  |  | Jeyasri
Profile Page |  |  | Jeyasri
Booking Page |  |  | Jeyasri
Reservation Page |  |  | Jeyasri
Search Page |  |  | Jeyasri
Book page (final page in booking process) |  |  | Jeyasri
Different pages for customer/admin |  |  | Jeyasri
List of Vehicles Page |  |  | Jeyasri
Individual Vehicle Page |  |  | Jeyasri
Add Vehicle Page |  |  | Jeyasri
List of User Page |  |  | Jeyasri
Individual User Page |  |  | Jeyasri
Add User Page |  |  | Jeyasri
List of Location Page |  |  | Jeyasri
Individual Location Page |  |  | Jeyasri
Add Location Page |  |  | Jeyasri
List of Reservation Page |  |  | Jeyasri
Add Reservation Page |  |  | Jeyasri
Unit test cases